## Budget Summary
Cost / Price Proposal from Mission Lift, LLC
Project: ABC Ageny's Youth Program
1 YEAR BUDGET |  |  | Phase 1 Planning | Phase 2 Data Collection | Phase 3 Data Analysis | Phase 4 Report
Personnel | Short Code | Rate / Day | Days | Days | Days | Days | Total Days | Total Cost
Lead Evaluator | EL | 800 | 1.0312 | 1.75 | 0.125 | 1.5 | 4.4062 | 3525
Secondary Evaluators | ES | 600 | 2.375 | 1.75 | 1.375 | 3.25 | 8.75 | 5250
Graphic Design | GD | 400 | 0 | 0 | 0 | 0.625 | 0.625 | 250
Editor | ED | 200 | 0 | 0 | 0 | 0.625 | 0.625 | 125
Research Assistant / Data Entry | DE | 160 | 0 | 0 | 0 | 0 | 0 | 0
Personnel Sub Total |  |  | 3.4062 | 3.5 | 1.5 | 6 | 14.4062 | 9150
Non Personnel Cost |  |  | Phase 1 Planning | Phase 2 Data Collection | Phase 3 Data Analysis | Phase 4 Report Prep | IN-KIND | COST TOTAL
Data Analysis Software: Qualtrics online survey software, N-Vivo and SPSS Subscription to research journals |  |  |  | 2000 |  |  | 2000 | 2000
Online database creation and support | TBD
Local travel for local conference | TBD | [6 empty] | 0
Non Personnel Sub Total |  |  | 0 | 2000 | 0 | 0 | 2000 | 2000
Mission Lift in-kind | [7 empty] | 2000
Evaluation Cost | [7 empty] | 9150
# of Projects | [7 empty] | 2
Unit Cost (per project) | [7 empty] | 4575

## Approach - Scope of Work
EVALUATION TECHNICAL APPROACH -SCOPE OF WORK
For ABC Agency
Hours
Item # | PLANNING & DESIGN - Deliverable | Calculation | Why Do This | Deadline | Lead Evaluator | Assistant Evaluator | Graphic Design | Editor | Research Assistant | PROJECT TOTAL | ABC Agency Personnel
1 | Finalize the scope and sign contractor agreement |  | Be on the same page | 2019-08-15 | 1 |  |  |  |  | 1 | 1
2 | Review grant and contract |  | Insure deadlines are met | 2019-08-20 | 2 |  |  |  |  | 2 | 0
3 | Literature Review to find similar comparison group and performance standard |  | Ability to compare results based on similar programs | 2018-08-30 |  | 3 |  |  |  | 3 | 0
4 | Review primary data collection tools - parent, activities log, Action plan benchmark implementation tracking index/log. Review and revise as needed pre and post profile to measure gains in knowledge, leadership and self efficacy, improved self, school leadership, self identity, self-care and wellness, goal attainment and community involvement. | development, client review | Stakeholders know what success looks like and activities correspond to outcomes; | 2018-08-20 | 0.5 | 3 |  |  |  | 3.5 | 1
5 | Obtain and review the evidence based models per grant proposal and obtain the assessment tools for any evidence based models. Develop a fidelity index |  | Ensure model implementation with fidelity | 2018-08-30 |  | 1 |  |  |  | 1 | 0
6 | Finalize logic model and theory of change |  | Get staff and coaches on the same page | 2018-08-10 | 0.5 | 2 |  |  |  | 2.5 | 0.5
7 | Develop an evaluation plan that includes process and outcome indicators. Include and outcome chart that show what is being measure, data source and frequency |  | Clear expectation of monitoring, learning and continuous improvement | 2018-08-30 | 1 | 4 |  |  |  | 5 | 0.5
8 | Beta testing survey instruments and translate to Spanish |  | Work out all the bugs | 2018-08-30 | 0.25 | 1.5 |  |  |  | 1.75 | 0.5
9 | Train staff on finalized evaluation plan and data collection methods | Mission Lift and client | Consistency on how to gather data and reduces bias | 2018-08-30 | 2 |  |  |  |  | 2 | 2
10 | Become a member of the National Implementation Research Network and the Implementation Drivers: Competency Drivers, Organization Drivers, and Leadership Drivers are identified |  | Gives access to national best practices | 2018-08-30 | 0.5 | 0.5 |  |  |  | 1 | 0.5
11 | Develop learning and evaluation committee monitoring activities, implementation drivers and associated performance bench marks and timelines |  | Ensure model implementation with fidelity | 2018-08-30 | 0.5 |  |  |  |  | 0.5 | 0.5
12 | Develop a data dash board for process, outcome indicators and completion index |  | Quick monitor of performance and implementation | 2018-09-15 |  | 4 |  |  |  | 4 | 0.5
| PLANNING SUBTOTAL |  |  |  | 8.25 | 19 | 0 | 0 | 0 | 27.25 | 7
| DATA COLLECTION: Using Primary and Secondary Sources |  | Outcome |  | Lead Evaluator | Assistant Evaluator | Graphic Design | Editor | Research Assistant | PROJECT TOTAL | ABC Agency Personnel
13 | Client communication and monthly with agency liaison - 1 hour monthly via email & Phone |  |  | ongoing | 12 | 0 | 0 | 0 | 0 | 12 | 2
14 | Obtain activities schedules and proof of completion | 1 hour x bi- monthly | Ensure program is being implemented as planned | monthly |  | 6 | 0 | 0 | 0 | 6 | 1
15 | Participate in the monthly benchmark meeting with Learning committee meetings with improvement cycle: plan, do, review, act |  | Ensure program is being implemented as planned | monthly | 12 | 0 | 0 | 0 | 0 | 12 | 12
16 | Administrator pre and post surveys to participating parent leaders |  | Track community impact | 5/15/19-6/30/19 | 0 | 3 | 0 | 0 | 0 | 0 | 20
17 | Review each parent file to ensure each has a personal goal, profile and other key documents |  | Consistent implementation across coaches | 2019-06-16 | 0 | 3 | 0 | 0 | 0 | 0 | 3
18 | Conduct 1 focus group or key stakeholder interview will be held with parents to receive qualitative feedback on how they that impacted |  | Highlight exemplary change in youth that represents coalition activities | 2019-06-20 | 2 | 2 | 0 | 0 | 0 | 4 | 0.5
| DATA COLLECTION SUBTOTAL |  |  |  | 14 | 14 | 0 | 0 | 0 | 34 | 38.5
| DATA ANALYSIS |  | Outcome |  | Lead Evaluator | Assistant Evaluator | Graphic Design | Editor | Data Entry | PROJECT TOTAL | ABC Agency Personnel
19 | Data entry of pre and post assessment, focus group impact survey (50 of each type) | 6 hours of interview and 50 surveys | Develops a longitudinal record of multi-year comparison | 10/18 & 6/19 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Data Cleaning (1 hour per survey instrument ) x 2 instruments | 3 hours | Eliminates typos and obvious incorrect answers | 2019-07-15 | 0 | 2 | 0 | 0 | 0 | 2 | 0
21 | Qualitative data analysis for common themes and triangularization; 0.5 hour per sector for open-ended questions | 4 hours | Reduces bias; Demonstrates common themes | 2019-07-20 | 1 | 4 | 0 | 0 | 0 | 5 | 0
22 | Comparative results based on segmentation of demographics; 1 hour survey instruments x 2 instrument | 3 hours | Find subgroup trends (i.e. men vs women) | 2019-07-20 | 0 | 3 | 0 | 0 | 0 | 3 | 0
23 | Statistical testing for correlation, cause and effect, cross tabulation for demographics and outcome indicator such as knowledge or leadership gain | SPSS for Anova, T-tests | Increase reliability of conclusions based on math rather than observation | 2019-07-20 | 0 | 2 | 0 | 0 | 0 | 2 | 0
| DATA ANALYSIS SUBTOTAL |  |  |  | 1 | 11 | 0 | 0 | 0 | 12 | 0
| REPORT WRITING & PRESENTATION |  | Outcome |  | Lead Evaluator | Assistant Evaluator | Graphic Design | Editor | Research Assistant | PROJECT TOTAL | ABC Agency Personnel
24 | Write final coalition-wide report including statistical tests and 1 high-level infographic report | 25 hours | Presents multiple year comparisons for public accountability and marketing; External evaluation increases future funding opportunities | 2018-07-30 | 1 | 3 | 0 | 2 | 0 | 6 | 0
25 | Present final report in person to leadership and parents for input and interpretation | 2 hours | Increases understanding; Collaborative recommendations created | 2019-07-30 | 3 | 3 | 0 | 0 | 0 | 6 | 2
26 | Develop model as a replicable toolkit |  | Replication and project scalability | 2019-07-30 | 6 | 18 | 5 | 3 | 0 | 32 | 2
27 | Participate in the a community meeting to discuss the findings and suggestions for steps moving forward |  | Be transparent to community & grant compliance | 2019-07-30 | 2 | 2 | 0 | 0 | 0 | 4 | 6
| REPORT SUB TOTAL |  |  |  | 12 | 26 | 5 | 5 | 0 | 48 | 10
| SUBTOTALS BY PERSONNEL | Hours | TOTAL HOURS FOR PROJECT |  | 35.25 | 70 | 5 | 5 | 0 | 121.25 | 55.5
|  | # of Days | TOTAL DAYS FOR PROJECT | DAYS | 4.4062 | 8.75 | 0.625 | 0.625 | 0 | 15.1562 | 6.9375